Patient Participation Action Plan

(As discuss with MMCPPG  20th March 2012) updated 1st May 2012

| Survey Finding | Agreed Action | Action by who | Action by when | Date completed or comments |
| --- | --- | --- | --- | --- |
| Problems with access to the telephone lines Their busy and constantly have to radial Kept waiting so incur cost especially pay as you go mobile | Improve communication to raise awareness how busy lines can be and what alternatives there are such as ringing at less busy time or using on line service if applicable | Practice to liaise with PPG members to raise awareness | 3 months | April 2012 Interim FAQ has been produced and displayed in surgery |
| Appointments’ not running to schedule | More efficient notification in the waiting room that surgeries are running late and by approximately how much. Notice by staff screen to remind to check time and amend the information bar. Better information to patients on reasons why appointments may not run to time by FAQ poster Developing a patient information booklet | Practice Manager PPG & Practice | Immediate 2 weeks FAQ Patient Booklet Initial 3mths completion 9mths | Staff training been undertaken situation being monitored Monitoring response to training at moment before implementing Completed 12.04.12 Existing booklet information being updated as a temporary stage so copies can be produced easier. Further development on future content ongoing |
|  | Possibility of booking double appointments for those who have complex needs, and better awareness of this availability by using the screen, making sure the surgery leaflet is available on reception and FAQ. Including information in a patient booklet. | Practice To check screen & leaflets available PPG | Initial phase FAQ – 2wks Booklet 9 mths | Completed 12.04.12 Surgery leaflet is available and frequently replenished. Screen update has been done See above |
| Survey Finding | Agreed Action | Action by who | Action by when | Date completed |
|  | Raise awareness of why appointments run over time by restarting FAQs on notice board to answer questions from the DES questionnaire | Practice & PPG | ASAP and will be ongoing rotating FAQ’S | Completed 12.04.12 |
| Just over 42% of respondents did not know about the telephone “Triage” service | Raise awareness of the service, what it is and how to use it. Explain what Triage is by FAQs on notice board and include in a booklet. | Practice & PPG | 2 weeks FAQ’s Booklet 9mths | Completed 12.04.12 See above |
| Request for blood tests to be available at the surgery | Visible details of the places where patients can obtain a blood test near to the surgery. Point out options by using FAQs, and the information screen. Information is already available but needs a better profile. | Practice & PPG | 2 weeks Inclusion in booklet 9 mths | Completed 12.04.12 List Updated 30th April See above |
| Some services requested on the survey are already available | Better awareness of services already provided in the surgery and how to access them by having pointers on the notice boards and examples of leaflets. To include access to free support courses in the City such as Living with Long Term Conditions, Cardiac rehab, V.I.P Carers course. Display on the PPG notice board | Practice & PPG | 1 week Inclusion in booklet 9 mths | Completed 12.04.12 Leaflets were checked. Notice of available service to be reprinted for the notice board and information screen. This will be monitored for changes See above |
| Toy’s in the clinic room to occupy or distract children | To look at suitable items after gaining suggestions from parents. | Practice | 6 months | Some progress has been made. Further work to be done |
| Review the confidentiality issues surrounding information exchanges at the front | Discuss issues with reception to ascertain the extent of problem and any suggestions for improvement. Notice on reception glass screen reminding patients they can ask to go somewhere private. Personal alarms to be available for staff, protocol adopted/reinforced | Practice manager | 4 weeks | Staff now aware of the issue and better use of quiet space being made. Notice for patients about the option for confidential purposes still to be produced and displayed Completed but monitoring display to be finished May |
| Survey Finding | Agreed Action | Action by who | Action by when | Date completed |
| To maintain the noticed improvement in the reception staff interaction with patients | Commend the improvement and discuss how the PRG and PPG can help maintain and improve the reception service. Notice PPG notice board giving survey result of improvement. Letter from PPG to staff. | PPG and reception staff | 2 weeks Immediate | Completed 04.12 Completed 06.04.12 Letter sent to staff from PPG – Future contact through PM re any issues. |
| Provision of alternative therapies such as acupuncture, physiotherapy etc | Discussions with the practice if any would be possible and if yes, develop a plan to introduce this service to the surgery. Discussions will need to be guided by local and national NHS changes | Practice & PPG for | 1 year | Reported that this is in discussion at the practice meetings but at the present time there is no capacity at the surgery to provide such services. The physical space will not allow, however this is to be monitored for future inclusion to services. |
| Improve the membership of the PRG and PPG by increasing numbers and representation of the practice population | Create an information presentation disc to be played on screen in the surgery. Work with the reception to increase the number of email participants in the PRG by at least 10% in the next 12 months Leaflet to go with repeat prescriptions which can also update patient contact details for the practice | To be looked at by practice & PPG PPG | Ongoing to be reviewed for progress quarterly | In discussion as to the practicality of this and possible content Completed 01.05.12 Small leaflet to be included in repeat prescriptions to update contact information and invite to join PRG Review quarterly |
| Automatic Entrance Doors | Research by the practice on options available to make access to the building easier for those with mobility problems and parents of young children. Discuss findings with PPG and make recommendations for funding opportunities | Practice Manager | High priority 9 months | Has been discussed at practice meetings and enquiries being made to cost and suitability. PPG offered to help in this process |